## Sprint Break Up
Post Details Page | Epic/ Module | Assignee Developer |  | Release | Sprint | Part | Priority | Category/ Component | Assignee | Development - Estd PH
Frontend HTML Development Part 1 | HTML Development |  |  | Release 2 | Sprint 1 | Product Application |  | HTML |  | 60
Frontend HTML Development Part 2 | HTML Development |  |  | Release 2 | Sprint 1 | Product Application |  | HTML |  | 60
QA Testing | HTML Development |  | Completed | Release 2 | Sprint 1 | Product Application |  | QA Testing |  | 20
Login | Admin - Authentication |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 1
Forgot Password | Admin - Authentication |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 1
Reset Password | Admin - Authentication |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 1
Logout from application | Admin - Authentication |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 1
View Candidate List | Admin - Dashboard |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 4
View Companies List | Admin - Dashboard |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 3
View Jobs List | Admin - Dashboard |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 3
Candidates List | Admin - Candidates |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 3
Search | Admin - Candidates |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 4
Candidate Details | Admin - Candidates |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 3
Block / Un Block Candidate Profile | Admin - Candidates |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 1
Company List | Admin - Company |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 2 | The list will be filtered with company name given by candidates .Company added by candidates will be linked with validated company by Admin and all company’s given by candidate will be updated with admin’s approved company .
Search | Admin - Company |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 2
Company Details | Admin - Company |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 3
View Company Jobs and Users applied | Admin - Company |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 4
Block / Unblock Company | Admin - Company |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 1
Training Video List | Admin - Training |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 4
Add New Training Video | Admin - Training |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 2
Edit Training Video | Admin - Training |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 2
Training Category List | Admin - Training |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 2
Add New Training Category | Admin - Training |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 6
Edit Training Category | Admin - Training |  | Completed | Release 2 | Sprint 2 | Admin Portal |  | Laravel |  | 6
QA Testing and Remediation | Laravel Testing |  |  | Release 2 | Sprint 2 | Product Application |  | QA Testing |  | 20
SPRINT - 3
Home Page | Admin - CMS Settings | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Privacy Policy | Admin - CMS Settings | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 2
Terms of use | Admin - CMS Settings | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 2
Contact us | Admin - CMS Settings | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 2
Tips | Admin - CMS Settings | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 6
Screening questions for Candidate registration | Admin - CMS Settings | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 6
MyHR Service Page | Admin - CMS Settings | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Subscription List | Admin - Subscription | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 3
Subscription Details | Admin - Subscription | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 3
Order List | Admin - Orders Management | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Order Details | Admin - Orders Management | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Order Status update | Admin - Orders Management | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 3
Candidate contact details | Admin - Orders Management | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Candidate information while subscription purchase | Admin - Orders Management | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 3
Download Payment reports | Admin - Orders Management | Israfil | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Reported Post List | Admin - Abuse Management | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Reported Post Details | Admin - Abuse Management | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
Reported Comments List | Admin - Abuse Management | Rumpa | Completed | Release 3 | Sprint 3 | Admin Portal |  | Laravel |  | 4
HTML Support for Admin | Admin - HTML |  | Completed | Release 3 | Sprint 3 | Admin Portal |  | HTML |  | 16
QA Testing and Remediation | Laravel Testing |  |  | Release 3 | Sprint 3 | Product Application |  | QA Testing |  | 30
SPRINT - 4
Faccebook Login | Register & Login | Israfil |  | Release 3 | Sprint 5 | Candidate Portal |  | Laravel |  | 2
Gmail Login | Register & Login | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
Basic Information while registering through Social Media | Register & Login | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 4
Email Registration | Register & Login | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 4
MCQ Screening | Register & Login | Rumpa |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
MCQ Screening answers | Register & Login | Rumpa |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 4
Login | Register & Login | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
Forgot Password | Register & Login | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
Reset Password | Register & Login | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
Email Verification Link | Register & Login | Rumpa |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 3
Login Verfication Check | Register & Login | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
Blocked by Admin | Register & Login | Rumpa |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 3
Create Profile (3 Step) | Profiles | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 6
View Profile | Profiles | Rumpa |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 3
Candidate Profile View *(Public) | Profiles | Rumpa |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 3
Update Profile | Profiles | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 4
Edit Uploaded CV and 30 sec video | Profiles | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 3
Activate / Deactivate / Delete Account | Profiles | Rumpa |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
Choose Background Image | Profiles | Israfil |  | Release 3 | Sprint 4 | Candidate Portal |  | Laravel |  | 2
Register | Signup & Login | Israfil |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 2
Admin Verification | Signup & Login | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Login | Signup & Login | Israfil |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Forgot Password | Signup & Login | Israfil |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Reset Password | Signup & Login | Israfil |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Email Verification | Signup & Login | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Pending Admin Verification(1.17) | Signup & Login | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Blocked by Admin(1.16) | Signup & Login | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Admin Approval Email | Signup & Login | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Admin Rejection Email | Signup & Login | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 1
Add Profile Information | Profile | Israfil |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 3
Add Company Profile information | Profile | Israfil |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 3
View Company Profile (5.7) | Profile | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 3
Update Profile | Profile | Israfil |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 3
View Followers | Profile | Rumpa |  | Release 3 | Sprint 4 | Employer Portal |  | Laravel |  | 2
QA Testing & Bugs Remediation | Laravel Testing |  |  | Release 3 | Sprint 4 | Product Application |  | QA Testing |  | 16
SPRINT - 5
Post a Job | Jobs | Israfil+Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 3
Screening Questions (Only one) | Jobs | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 6
Surprise Question | Jobs | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 5
Job Lists | Jobs | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 4
Job Details | Jobs | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 3
Applied Candidates(7.8) | Jobs | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 3
Send Message Candidates (7.9) | Jobs | Israfil |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 2
Download Resume (7.10) (6.5) | Jobs | Israfil |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 1
Candidate Profile (Ref: Candidate Profile in Candidate frontend)(6.3) | Jobs | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 1
Create Post (4.1) | Dashboard | Israfil |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 2
View the post(4.2) | Dashboard | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 2
Report a Comment (4.9) | Dashboard | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 2
Search Candidate (6.1) | Dashboard | Israfil+Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 6
Candidate Lists (6.2) | Dashboard | Israfil+Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 3
Candidate Profile (Ref: Candidate Profile in Candidate frontend) | Dashboard | Israfil |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 2
Contact Candidates (6.4)(3.3) | Dashboard | Israfil |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 3
Download Resume (7.10) (6.5) | Dashboard | Rumpa |  | Release 3 | Sprint 5 | Employer Portal |  | Laravel |  | 1
QA Testing & Bugs Remediation | Laravel Testing |  |  | Release 3 | Sprint 5 | Product Application |  | QA Testing |  | 16
SPRINT - 6
Contact List (Recently Communicated) 3.2 | Message | Israfil |  | Release 4 | Sprint 6 | Employer Portal |  | Laravel |  | 2 |  | https://uiplonline.com/my-hr-web/New-html/messages.html
Message Thread | Message | Israfil |  | Release 4 | Sprint 6 | Employer Portal |  | Laravel |  | 4
Send Message to Candidates.(3.3) | Message | Israfil |  | Release 4 | Sprint 6 | Employer Portal |  | Laravel |  | 2
Block Candidates from sending messages.3.6 | Message | Israfil |  | Release 4 | Sprint 6 | Employer Portal |  | Laravel |  | 0.5
Contact List (Recently Communicated)(3.2) | Message | Israfil |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 7
Send message to any candidate profile(3.3) | Message | Israfil |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 4
Reply to messages from companies(3.4) | Message | Israfil |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 4
Message Thread(3.5) | Message | Israfil |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 4
Block Candidates from sending message.( 3.6) | Message | Israfil |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 2
Company List (Recently Communicated)(MESSAGE MODULE)3.1,3.2,3.3 | Message | Israfil |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 4 |  | https://uiplonline.com/my-hr-web/New-html/company-list.html
Home Page | Miscellaneous | Rumpa |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 4 |  | https://uiplonline.com/my-hr-web/New-html/index.html
Privacy Policy | Miscellaneous | Rumpa |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 2 |  | http://uiplonline.com/my-hr-web/New-html/privacy.html
Terms of use | Miscellaneous | Rumpa |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 2 |  | http://uiplonline.com/my-hr-web/New-html/terms.html
Contact us | Miscellaneous | Rumpa |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 4 |  | http://uiplonline.com/my-hr-web/New-html/contact.html
About Us | Miscellaneous | Rumpa |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 2 |  | http://uiplonline.com/my-hr-web/New-html/about.html
Tips | Miscellaneous | Rumpa |  | Release 4 | Sprint 6 | Candidate Portal |  | Laravel |  | 2 |  | http://uiplonline.com/my-hr-web/New-html/tips.html
QA Testing & Bugs Remediation | Laravel Testing |  |  | Release 4 | Sprint 6 | Product Application |  | QA Testing |  | 16
SPRINT - 7
Dashboard/Home | Dashboard/Home |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 8
Create Post (Text) | Dashboard/Home |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 2
Create Post (Image) | Dashboard/Home |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 5
Create Post (Video) | Dashboard/Home |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 5
Post Details Page 4.6 | Dashboard/Home | Rumpa |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 4 | 4
Post Likes & Share | Dashboard/Home | Rumpa |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 3 | 2+3 = 5
Post Comment 4.8 | Dashboard/Home | Rumpa |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 3 | 3
Report a comment | Dashboard/Home |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 3 | 3
Report a Post | Dashboard/Home |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 3 | 3
Search Profile | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 3 | 4
List Profiles | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 6 | 6
Connection Request | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 4
Follow Candidate | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 4
Following List | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 4 | 4
Follow Company 5.6 | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 3
Company Page 5.7 | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 4 | 4
Candidate Page 5.8 | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 4 | 4
Accept/ Reject Connection Requests 5.10 | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 3
Report a Company | Network |  |  | Release 4 | Sprint 7 | Candidate Portal |  | Laravel |  | 2 | 2
QA Testing & Bugs Remediation | Laravel Testing |  |  | Release 4 | Sprint 7 | Product Application |  | QA Testing |  | 16
SPRINT - 8
Search Jobs | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 5
Job Alert | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 3
Job List | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 4
Job Details | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 4
Apply Job - Outside My HR Portal | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 1
Apply Job - Inside My HR Portal | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 2
Save Job | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 2
Specific Question | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 4
Surprise Question | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 6
Subscribe for Alerts on search parameter | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 3
Job Alerts Email | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 3
Manage Alerts | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 4
Page for view all alerts and delete | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 3
Share Jobs | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 2
Tips page - Interview Question | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 2
Cron job to change job status | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 2
Save job as Draft at the time of apply | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 6
Save job as Draft List | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 4
Check Job Status for saved jobs | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 4
Reminder Mail on Saved as Draft Jobs | Jobs |  |  | Release 5 | Sprint 8 | Candidate Portal |  | Laravel |  | 1.5
QA Testing & Bugs Remediation | Laravel Testing |  |  | Release 5 | Sprint 8 | Product Application |  | QA Testing |  | 16
SPRINT - 9
List of Training Videos | Training |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 6
Details of Training Videos | Training |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 8
List of Services | My HR Services (Premium Service Purchase) |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 2
Service Selection | My HR Services (Premium Service Purchase) |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 2
Admin Action for Services | My HR Services (Premium Service Purchase) |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 1
Payment Gateway | My HR Services (Premium Service Purchase) |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 2
Purchase form | My HR Services (Premium Service Purchase) |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 4
In App Notification | Notifications |  |  | Release 5 | Sprint 9 | All Portal |  | Laravel |  | 4
Email Notification | Notifications |  |  | Release 5 | Sprint 9 | All Portal |  | Laravel |  | 5
Notification Lists | Notifications |  |  | Release 5 | Sprint 9 | All Portal |  | Laravel |  | 5
Message Notifications | Notifications |  |  | Release 5 | Sprint 9 | All Portal |  | Laravel |  | 4
Language switch | Multilingual |  |  | Release 5 | Sprint 9 | Employer Portal |  | Laravel |  | 2
Language Available | Multilingual |  |  | Release 5 | Sprint 9 | Employer Portal |  | Laravel |  | 4
Language switch | Multilingual |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 2
Language Available | Multilingual |  |  | Release 5 | Sprint 9 | Candidate Portal |  | Laravel |  | 4
QA Testing & Bugs Remediation | Laravel Testing |  |  | Release 5 | Sprint 9 | Product Application |  | QA Testing |  | 32
Live Server Deployment | Go Live (Alpha) |  |  | Release 6 |  | All Portal |  | Server Admin |  | 4
Note on A114: Dear +subhajyoti@unifiedinfotech.net daa i can not find page regarding this story _Assigned to Subhajyoti Sinha Roy_ -Israfil Hashmi

## Sheet2
Release | Sprint | Sprint Days | Start Date | End Date
Release 2 | Sprint 1 | 20 | 2020-02-04 | 2020-03-05
| Sprint 2 | 6 | 2020-03-09 | 2020-03-17
Release 3 | Sprint 3 | 10 | 2020-03-19 | 2020-04-03
| Sprint 4 | 7 | 2020-04-07 | 2020-04-16
| Sprint 5 | 5 | 2020-04-20 | 2020-04-27
Release 4 | Sprint 6 | 5 | 2020-04-29 | 2020-05-06
| Sprint 7 | 5 | 2020-05-08 | 2020-05-18
Release 5 | Sprint 8 | 7 | 2020-05-20 | 2020-06-01
| Sprint 9 | 9 | 2020-06-03 | 2020-06-17
Release 6 |  | 1 | 2020-06-19 | 2020-06-23
Grand Total

## Sheet3
Report a Company 5.11